## Sheet1
ANOTHER | GAME | STUDIO
SPRINT # 1 | Category | BackLog / User Stories | To Do | Started on (Date) | In Progress/ Due | Testing | Priority | Done | Member Responsible | Hours invested so far | Current Status
| Type of game | Horror / Puzzle | N/A | 2018-02-02 | Completed | N/A |  | Yes | Team |  | Completed
| Controllers | Controller Input | Decide which type | 2018-02-02 | Due Thursday Feb/8 | Test on build TBA | High | Yes | Team | 2 Hours | Completed
| Art Assets environment | Asylum, Haunted House… | Find assets | 2018-02-02 | Due Tuesday Feb/6 | N/A | High | No | Team | TBA | In progress
| Sound | Environment sounds | Sample sound assets | 2018-02-02 | Due Thursday Feb/8 | Test during meeting | High | No | Andre Reano/ Team | TBA | Not Started
| Art Enemies | Zombies, Aliens, Ghosts | Determine the type | 2018-02-02 | Due Thursday Feb/8 | N/A | High | No | Andre, John, Logan | TBA | Not Started
| Story | Back story of the game | Full story of the game | 2018-02-02 | Due Thursday Feb/8 | Discuss during meeting | High | No | Andre, John, Logan | TBA | Completed
| Level Design | Blueprint of level | Level Draft | 2018-02-02 | Due Thursday Feb/8 | Discuss during meeting | Medium | No | Andre Reano | 1 Hour | Researching
| UI | Type of UI | UI Design | 2018-02-02 | Due Thursday Feb/8 | Discuss during meeting | Medium | No | Taha Saleem | 1 Hour | In progress
Research
| Game Mechanics | Stealth Mechanic | Stealth/AI research | ? | Due Thursday Feb/8 | Disscuss progress | Medium | No | John Zhu | TBA | Not Started
| Weapons | Implementation of weapon | Inventory interaction | 2/4/2018 | Due Thursday Feb/8 | Disscuss progress | Medium | No | Taha Saleem | 30 Mins | In Progress
| Player input | Touch/Throw Interact | Input from Controller | ? | Due Thursday Feb/8 | Disscuss progress | High | Yes | Anto ,Ivan | TBA | Not Started
| Horror Games samples | Reference games | List sample games | ? | Due Thursday Feb/8 | Disscuss progress | Low | No | John, Logan | TBA | Not Started
Meeting Summary
Main Character: Father Mathews, runs the orphanage and got naughty with (unknown) now he has to pay the consequences dealing with his Omen child
Game Setting: Boarding School Orphanage (Victorian Setting) Games used as reference: Layers of Fear and Amnesia (Get Anto to play these :)
Game Starts: Kid approaches Mathews and asks if he wants to play a game (Watch Saw I II III IV…..XXXX for reference to how to say this) Mathews faints and wakes up in his nightmare ( 7 years of child support debt)
Level Design: Will include 3 floors with a variaty of rooms, including infirmary, basement etc. Access to the next stage will be granted after solving a puzzle
Tasks: Each member of the team will create a puzzle of their like, also as specified 3 Anticipation and jump scare moments.
Controllers: Main game controllers will be the Oculus controllers, testing and/or secondary controllers will be keyboard and mouse
UI: We will avoid as much as possible to add text to the screen. Players health will be on the display queues of damage will be implied with the screen turning greyish and heart beat
Inventory: Player will pull a bag and pick an item or put items in it grabbing them with their hand. Player will have to hold a lamp with one hand and one other item on the other hand.
SPRINT#2 | Category | BackLog / User Stories | To Do | Started on (Date) | In Progress/ Due | Testing | Priority | Done | Member Responsible | Hours invested so far | Current Status
| Controllers | Controller Input | Keyboard/Mouse inpt | 2018-02-09 | Due Friday Feb/16 | Test on build TBA | High | Yes | Anto Nanahji | TBA | Not Started
| Controllers | Controller Input | Oculus Input | 2018-02-09 | Due Friday Feb/16 | Test on build TBA | High | No | Ivan Echavaria | 3 hours | To be pushed
| Art Assets environment | Victorian House Type | Find assets | 2018-02-09 | Due Friday Feb/16 | N/A | High | No | Taha/Logan | 1Hour+TS | TS
| Sound | Game Over/ Main Screen | Find Sounds | 2018-02-09 | Due Friday Feb/16 | N/A | High | No | Taha Saleem | 30 min | Need voting TS
| Sound FX | Steps/Breathing/Screams | Find Sound FXs | 2018-02-09 | Due Friday Feb/16 | N/A | High | No | Logan King | TBA | Not Started
| Art Enemies | Orphans , ghostly kids etc | Find assets | 2018-02-09 | Due Friday Feb/16 | N/A | High | No | Taha/Logan | TBA | Not Started
| Level Design | Blueprint of level | Actual Level Design | 2018-02-09 | Due Friday Feb/16 | In progress | High | No | Andre Reano | 1 Hour+ | Drawing
| Level Puzzles | Create a puzzle | 6 Puzzles | 2018-02-09 | Due Friday Feb/16 | TBA | Medium | No | Team | IF completed add initial-> | TS-AR
| Anticipation moments | Create anticipation | Scare anticipation | 2018-02-09 | Due Friday Feb/16 | TBA | Medium | No | Andre, John, Taha | IF completed add initial-> | TS-AR
| Jump Scare | Create a jump scare | Jump Scare | 2018-02-09 | Due Friday Feb/16 | TBA | Medium | No | Anto, Ivan, Logan | IF completed add initial-> | Add initials here.
| AI | Implement enemy AI | Enemy AI | 2018-02-09 | On Going | TAB | Medium | No | John Zhu | TBA | Not Started
To Implement at some point
| Game UI | Screens UI | Screens Design |  | TBA | TBA | Low | No | TBA |  | Not Started
| In Game UI | Inventory, Health reaction | Inventory / Player UI |  | TBA | TBA | Low | No | TBA |  | Will be split in two
| Art objects | Items, Lamps, etc | interactable items |  | TBA | TBA | Low | No | Team |  | Not Started
| Story Dialog | Record sound of voice | Game Voices |  | TBA | TBA | Low | No | John Zhu |  | Not Started
Note on K2: Ivan E.: Add hours invested in this, so I can know if you need assistance and add one more person to it, add current + previous
Note on L2: Ivan E.: Add the current status where you are at from the due date so we can modify if necessary for next sprint
Note on C3: Ivan E.: Everyone has agreed to go with a Horror,Puzzle game. I think we can move on from this
Note on C4: Ivan E.: With the AI implementation and the fact that we can use Oculus we will use the controllers to move the player.
Note on D4: Ivan E.: Due motion sickness, we have to determine whether or not we will teleport in the game or use joystick to move around, we will talk about this again in our next meeting
Note on C5: Ivan E.: As per the meeting, everyone is looking for assets that will match our game theme, Asylum, haunted house, abandone hospital, low poly, whichever category we get the most assets from wins
Note on C6: Ivan E.: Must match the theme of the game, sounds include enviroment sounds, and sound queues like screams, crawling, breathing, doors closing/opening etc. This is mainly Andres but anyone who thinks that may find something that can go with the game can pitch in
Note on D6: Ivan E.: Assets found will be discussed during our meeting on Thursday, we will decide whether they work or not completely for the game
Note on C7: Ivan E.: Bases on the story of the game we will need to find assets that match
Note on C8: Ivan E.: Andre, John and Logan, will determine what is the best story setting for our game based on the theme
Note on C9: Ivan E.: Bases on our story, create the level in which we will be playing , a blueprint of the level so we can discuss gameplay in our next meeting
Note on H9: Ivan E.: As this will be discuss it will/ could be changed
Note on C10: Ivan E.: As per the Theme of the game, check what would be the best UI during gameplay, also a draft design of the Title, win and end
Note on H10: Ivan E.: Will/Could be changed during our meeting
Note on C13: Ivan E.: Stealth Mechanic will have to be researched with the AI implementation. Enemies noticing noise or character location Waiting for the coast to be cleared
Note on C14: Ivan E.: Research how can we select, equip or store weapon or objects we find in the game
Note on C15: Ivan E.: How can we get input from the controllers and how to implement the visual hands position in the game
Note on C16: Ivan E.: Find references to games we can take as example to match our game's aesthetics
Note on J16: Ivan E.: Whoever has experience with horror games can pitch in into this
Note on K27: Ivan E.: Add hours invested in this, so I can know if you need assistance and add one more person to it, add current + previous
Note on L27: Ivan E.: Add the current status where you are at from the due date so we can modify if necessary for next sprint
Note on C28: Ivan E.: Main Input: Oculus Controllers Test/Secondary Input: KeyBoard - Mouse
Note on D28: Ivan E.: Create input controllers for testing game and to play the game.
Note on J28: Ivan E.: Anto : Keyboard/ Mouse input Ivan : Oculus input
Note on C29: Ivan E.: Main Input: Oculus Controllers Test/Secondary Input: KeyBoard - Mouse
Note on D29: Ivan E.: Create input controllers for testing game and to play the game.
Note on J29: Ivan E.: Anto : Keyboard/ Mouse input Ivan : Oculus input
Note on C30: Ivan E.: Art assets: Manor, Infirmary, Victorian. Reference Games: Layers of Fear Amnesia
Note on J30: Ivan E.: Find the actual assets that would match our game and add it to the Shared drive
Note on C31: Ivan E.: Find Background music for Game Over, Main Screen, In game music
Note on J31: Ivan E.: Colaborate with Logan who has SFX
Note on C32: Ivan E.: Find sound FXs for the game, involving steps, doors opening, close, desk moving, children laugh, wood squeak etc
Note on C33: Ivan E.: Find the type of enemies we decided to go with, most are children, hopefully with some animations
Note on J33: Ivan E.: Find the actual assets that would match our game and add it to the Shared drive
Note on C34: Ivan E.: Actual Game Levels, involving 3 floors (basement, Main floor, infirmary , attic) also be minful of the puzzles to come that will allow the player to move forward (6 puzzles) set their positions Include possible positions for Anticipation and jump scares
Note on C35: Ivan E.: Each team member will create a puzzle of their like involving the theme of the game. Be Mindful of the puzzle created as each person will be responsible for implementing it. Add a word documents with how the puzzle will work to the respective folder
Note on C36: Ivan E.: John Andre Taha Create an anticipation (Holy shit holy shit holy shit!) moment for the player Add a work document to the respective folder or with your puzzle
Note on C37: Ivan E.: Logan Ivan Anto Create a jump scare moment for the game Add a word document to the respective folder or with your puzzle doc
Note on C38: Ivan E.: Enemy Attacks, hunt or try to find player or reacts to sounds etc
Note on C41: Ivan E.: Splash screen, Main Title, Game Over and win.
Note on C42: Ivan E.: Implementation of damage and damage reaction for UI Implementation of Inventory UI and usability
Note on C44: Ivan E.: Record sound of voice telling the player the story of the game when they pick the note Also voice of characters that talk to the player